## Project Tracker
Task ID | Project | Department | Task / Deliverable | Owner | Priority | Status | Progress (%) | Start Date | Due Date | Days to Due | Overdue? | Last Update | Blocker / Notes
TASK-001 | Sales Performance Analytics | Data & Analytics | Mengumpulkan kebutuhan data | Budi Santoso | Medium | In Progress | 79 | 2026-09-05 | 2026-11-23 | 24 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-002 | PMO Transformation | Project Management | Menyusun project charter | Citra Amelia | Critical | In Progress | 35 | 2026-08-28 | 2026-11-03 | 4 | No | 2026-10-27 | Sedang dikerjakan
TASK-003 | Support Process Improvement | Customer Success | Memantau SLA respons | Rizky Maulana | Medium | Completed | 100 | 2026-08-01 | 2026-11-04 | 5 | No | 2026-10-25 | Selesai sesuai rencana
TASK-004 | Data Quality Initiative | Data & Analytics | Membersihkan dataset operasional | Kevin Hartono | Medium | Completed | 100 | 2026-08-13 | 2026-11-20 | 21 | No | 2026-10-29 | Dokumentasi telah diperbarui
TASK-005 | Service Delivery Improvement | Operations | Memeriksa checklist operasional | Aldi Wijaya | Low | In Review | 91 | 2026-09-07 | 2026-11-15 | 16 | No | 2026-10-29 | Menunggu review stakeholder
TASK-006 | Enterprise Process Improvement | Project Management | Mengidentifikasi risiko proyek | Kevin Hartono | High | In Progress | 45 | 2026-08-11 | 2026-10-22 | -8 | Yes | 2026-10-25 | Koordinasi lintas tim berlangsung
TASK-007 | Internal Workflow Automation | Product & Engineering | Menulis unit test | Putri Ananda | Low | In Progress | 19 | 2026-08-27 | 2026-12-05 | 36 | No | 2026-10-28 | Koordinasi lintas tim berlangsung
TASK-008 | Digital Marketing Optimization | Marketing & Communications | Menyiapkan materi kampanye | Dimas Saputra | Medium | Completed | 100 | 2026-09-18 | 2026-12-09 | 40 | No | 2026-10-27 | Selesai sesuai rencana
TASK-009 | Enterprise Process Improvement | Project Management | Menyiapkan rapat steering committee | Fajar Nugroho | Low | In Progress | 50 | 2026-09-04 | 2026-11-22 | 23 | No | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-010 | Operational Excellence | Operations | Menyelesaikan tiket internal | Aldi Wijaya | Medium | In Progress | 43 | 2026-09-03 | 2026-11-26 | 27 | No | 2026-10-24 | Sedang dikerjakan
TASK-011 | Talent Acquisition Sprint | Human Resources | Memperbarui database pelatihan | Dewi Lestari | Critical | Not Started | 0 | 2026-10-05 | 2026-12-06 | 37 | No | 2026-10-28 | Menunggu prioritas sprint
TASK-012 | Operational Excellence | Operations | Menyusun laporan operasional | Citra Amelia | Medium | In Review | 88 | 2026-09-19 | 2026-11-07 | 8 | No | 2026-10-29 | Menunggu review stakeholder
TASK-013 | Procurement Efficiency | Finance & Procurement | Melakukan rekonsiliasi biaya | Rafi Hidayat | Critical | In Progress | 43 | 2026-09-07 | 2026-11-30 | 31 | No | 2026-10-29 | Sesuai rencana kerja
TASK-014 | Vendor Management | Finance & Procurement | Meninjau kontrak vendor | Andi Pratama | High | In Progress | 77 | 2026-08-26 | 2026-10-27 | -3 | Yes | 2026-10-25 | Koordinasi lintas tim berlangsung
TASK-015 | Customer Experience Program | Customer Success | Menindaklanjuti permintaan pelanggan | Budi Santoso | High | Completed | 100 | 2026-09-16 | 2026-11-10 | 11 | No | 2026-10-23 | Dokumentasi telah diperbarui
TASK-016 | Business Intelligence Dashboard | Data & Analytics | Melakukan rekonsiliasi data | Rafi Hidayat | Medium | In Progress | 43 | 2026-08-17 | 2026-11-07 | 8 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-017 | Corporate Communications | Marketing & Communications | Meninjau brand guideline | Kevin Hartono | Low | In Progress | 57 | 2026-08-26 | 2026-11-15 | 16 | No | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-018 | Business Intelligence Dashboard | Data & Analytics | Menyusun definisi KPI | Aldi Wijaya | Medium | Not Started | 0 | 2026-08-09 | 2026-12-09 | 40 | No | 2026-10-30 | Menunggu prioritas sprint
TASK-019 | Business Intelligence Dashboard | Data & Analytics | Mengumpulkan kebutuhan data | Lia Maharani | Critical | Completed | 100 | 2026-08-09 | 2026-11-07 | 8 | No | 2026-10-28 | Selesai sesuai rencana
TASK-020 | Support Process Improvement | Customer Success | Menyiapkan laporan kepuasan pelanggan | Rina Kurnia | Medium | Not Started | 0 | 2026-09-22 | 2026-11-05 | 6 | No | 2026-10-24 | Belum dimulai; masuk backlog
TASK-021 | Client Onboarding | Customer Success | Menindaklanjuti permintaan pelanggan | Intan Permata | High | In Progress | 23 | 2026-08-13 | 2026-10-27 | -3 | Yes | 2026-10-27 | Sesuai rencana kerja
TASK-022 | Support Process Improvement | Customer Success | Memperbarui knowledge base | Kevin Hartono | Low | In Progress | 19 | 2026-08-24 | 2026-10-31 | 1 | No | 2026-10-29 | Koordinasi lintas tim berlangsung
TASK-023 | PMO Transformation | Project Management | Memvalidasi scope pekerjaan | Fajar Nugroho | High | Completed | 92 | 2026-08-12 | 2026-11-04 | 5 | No | 2026-10-30 | Deliverable sudah diserahkan
TASK-024 | Customer Portal Revamp | Product & Engineering | Melakukan regression testing | Citra Amelia | Medium | Completed | 89 | 2026-09-19 | 2026-11-10 | 11 | No | 2026-10-23 | Dokumentasi telah diperbarui
TASK-025 | Internal Workflow Automation | Product & Engineering | Melakukan code review | Siti Rahma | Medium | In Review | 90 | 2026-08-28 | 2026-12-12 | 43 | No | 2026-10-23 | Menunggu review stakeholder
TASK-026 | Platform Reliability | Product & Engineering | Menyusun user story | Yoga Firmansyah | Medium | In Progress | 40 | 2026-08-11 | 2026-10-22 | -8 | Yes | 2026-10-27 | Sesuai rencana kerja
TASK-027 | PMO Transformation | Project Management | Menyiapkan laporan milestone | Fajar Nugroho | Medium | In Review | 88 | 2026-09-23 | 2026-11-21 | 22 | No | 2026-10-25 | Draft siap ditinjau
TASK-028 | Digital Marketing Optimization | Marketing & Communications | Memperbarui landing page | Andi Pratama | Medium | In Review | 82 | 2026-08-17 | 2026-12-06 | 37 | No | 2026-10-29 | Perlu validasi akhir
TASK-029 | Business Intelligence Dashboard | Data & Analytics | Melakukan rekonsiliasi data | Intan Permata | High | In Progress | 18 | 2026-10-04 | 2026-11-09 | 10 | No | 2026-10-26 | Sedang dikerjakan
TASK-030 | Platform Reliability | Product & Engineering | Memperbarui dokumentasi teknis | Citra Amelia | Medium | Completed | 100 | 2026-09-08 | 2026-11-23 | 24 | No | 2026-10-29 | Deliverable sudah diserahkan
TASK-031 | Customer Portal Revamp | Product & Engineering | Memperbaiki bug prioritas tinggi | Dimas Saputra | High | In Progress | 36 | 2026-08-14 | 2026-11-15 | 16 | No | 2026-10-26 | Sesuai rencana kerja
TASK-032 | Customer Experience Program | Customer Success | Memantau tiket dukungan | Dimas Saputra | High | In Progress | 10 | 2026-08-12 | 2026-11-09 | 10 | No | 2026-10-26 | Sesuai rencana kerja
TASK-033 | Platform Reliability | Product & Engineering | Memperbarui dokumentasi teknis | Rizky Maulana | Critical | Not Started | 0 | 2026-09-24 | 2026-10-25 | -5 | Yes | 2026-10-30 | Perlu konfirmasi ruang lingkup
TASK-034 | Performance Management | Human Resources | Menyusun laporan HR bulanan | Siti Rahma | High | Not Started | 0 | 2026-08-19 | 2026-12-01 | 32 | No | 2026-10-27 | Belum dimulai; masuk backlog
TASK-035 | Digital Marketing Optimization | Marketing & Communications | Menulis draft artikel | Intan Permata | Medium | In Progress | 29 | 2026-10-11 | 2026-11-19 | 20 | No | 2026-10-28 | Sesuai rencana kerja
TASK-036 | Operational Excellence | Operations | Memperbarui SOP operasional | Agus Setiawan | Medium | Completed | 100 | 2026-09-12 | 2026-11-10 | 11 | No | 2026-10-29 | Selesai sesuai rencana
TASK-037 | SOP Standardization | Operations | Memperbarui SOP operasional | Intan Permata | Medium | Completed | 100 | 2026-08-29 | 2026-12-04 | 35 | No | 2026-10-27 | Selesai sesuai rencana
TASK-038 | SOP Standardization | Operations | Melakukan inspeksi proses | Citra Amelia | Medium | In Progress | 61 | 2026-08-09 | 2026-11-07 | 8 | No | 2026-10-30 | Sedang dikerjakan
TASK-039 | Business Intelligence Dashboard | Data & Analytics | Membangun dashboard monitoring | Rina Kurnia | Medium | Not Started | 0 | 2026-10-14 | 2026-10-28 | -2 | Yes | 2026-10-25 | Perlu konfirmasi ruang lingkup
TASK-040 | Service Delivery Improvement | Operations | Menyusun laporan operasional | Andi Pratama | High | Completed | 85 | 2026-08-15 | 2026-11-17 | 18 | No | 2026-10-27 | Dokumentasi telah diperbarui
TASK-041 | Talent Acquisition Sprint | Human Resources | Memeriksa kelengkapan dokumen HR | Rafi Hidayat | Medium | In Progress | 48 | 2026-09-12 | 2026-11-28 | 29 | No | 2026-10-24 | Sedang dikerjakan
TASK-042 | Performance Management | Human Resources | Memeriksa kelengkapan dokumen HR | Yoga Firmansyah | Medium | Not Started | 0 | 2026-09-07 | 2026-11-04 | 5 | No | 2026-10-28 | Perlu konfirmasi ruang lingkup
TASK-043 | Vendor Management | Finance & Procurement | Memproses reimbursement | Putri Ananda | Medium | In Progress | 84 | 2026-08-01 | 2026-10-28 | -2 | Yes | 2026-10-25 | Koordinasi lintas tim berlangsung
TASK-044 | Support Process Improvement | Customer Success | Memvalidasi penyelesaian keluhan | Budi Santoso | Low | In Progress | 31 | 2026-08-28 | 2026-12-02 | 33 | No | 2026-10-25 | Sedang dikerjakan
TASK-045 | Sales Performance Analytics | Data & Analytics | Menyusun definisi KPI | Lia Maharani | High | Completed | 100 | 2026-09-09 | 2026-11-09 | 10 | No | 2026-10-29 | Dokumentasi telah diperbarui
TASK-046 | Client Onboarding | Customer Success | Menjadwalkan sesi training pelanggan | Intan Permata | Medium | In Review | 92 | 2026-10-13 | 2026-11-24 | 25 | No | 2026-10-30 | Menunggu review stakeholder
TASK-047 | Business Intelligence Dashboard | Data & Analytics | Menganalisis tren kinerja | Dewi Lestari | Medium | Completed | 100 | 2026-08-23 | 2026-10-29 | -1 | No | 2026-10-28 | Deliverable sudah diserahkan
TASK-048 | Client Onboarding | Customer Success | Menyusun rencana tindak lanjut akun | Citra Amelia | Medium | Completed | 96 | 2026-09-10 | 2026-11-05 | 6 | No | 2026-10-28 | Deliverable sudah diserahkan
TASK-049 | Support Process Improvement | Customer Success | Memvalidasi penyelesaian keluhan | Lia Maharani | Medium | In Review | 96 | 2026-09-01 | 2026-10-29 | -1 | Yes | 2026-10-27 | Draft siap ditinjau
TASK-050 | Procurement Efficiency | Finance & Procurement | Memperbarui cash-flow forecast | Budi Santoso | High | In Progress | 79 | 2026-09-06 | 2026-10-31 | 1 | No | 2026-10-28 | Sesuai rencana kerja
TASK-051 | Corporate Communications | Marketing & Communications | Menyiapkan materi media sosial | Citra Amelia | Medium | In Progress | 52 | 2026-08-20 | 2026-10-25 | -5 | Yes | 2026-10-24 | Sedang dikerjakan
TASK-052 | Enterprise Process Improvement | Project Management | Mengidentifikasi risiko proyek | Yoga Firmansyah | Medium | In Review | 98 | 2026-09-19 | 2026-10-23 | -7 | Yes | 2026-10-30 | Perlu validasi akhir
TASK-053 | Learning & Development | Human Resources | Mengumpulkan feedback karyawan | Intan Permata | Medium | Blocked | 48 | 2026-09-23 | 2026-11-18 | 19 | No | 2026-10-27 | Dependensi vendor belum selesai
TASK-054 | Budget Control Initiative | Finance & Procurement | Memproses reimbursement | Nadia Putri | Medium | In Progress | 61 | 2026-08-04 | 2026-11-14 | 15 | No | 2026-10-28 | Sedang dikerjakan
TASK-055 | Annual Planning | Project Management | Mencatat keputusan rapat | Rizky Maulana | Medium | Not Started | 0 | 2026-10-12 | 2026-10-31 | 1 | No | 2026-10-28 | Belum dimulai; masuk backlog
TASK-056 | Enterprise Process Improvement | Project Management | Memperbarui risk register | Agus Setiawan | High | In Progress | 58 | 2026-09-11 | 2026-12-05 | 36 | No | 2026-10-26 | Sedang dikerjakan
TASK-057 | Business Intelligence Dashboard | Data & Analytics | Mendokumentasikan data dictionary | Siti Rahma | High | Completed | 100 | 2026-10-09 | 2026-10-22 | -8 | No | 2026-10-27 | Selesai sesuai rencana
TASK-058 | Corporate Communications | Marketing & Communications | Menyusun kalender konten | Aldi Wijaya | Medium | Not Started | 0 | 2026-08-20 | 2026-11-19 | 20 | No | 2026-10-23 | Menunggu prioritas sprint
TASK-059 | Procurement Efficiency | Finance & Procurement | Melakukan rekonsiliasi biaya | Maya Anggraini | Low | Completed | 100 | 2026-08-15 | 2026-11-25 | 26 | No | 2026-10-24 | Dokumentasi telah diperbarui
TASK-060 | Operational Excellence | Operations | Memantau SLA layanan | Putri Ananda | High | Completed | 100 | 2026-10-15 | 2026-12-11 | 42 | No | 2026-10-30 | Selesai sesuai rencana
TASK-061 | Learning & Development | Human Resources | Menyiapkan evaluasi kinerja | Lia Maharani | High | In Progress | 63 | 2026-09-17 | 2026-10-22 | -8 | Yes | 2026-10-24 | Sesuai rencana kerja
TASK-062 | Performance Management | Human Resources | Memantau target rekrutmen | Putri Ananda | Medium | In Progress | 44 | 2026-08-20 | 2026-12-05 | 36 | No | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-063 | Client Onboarding | Customer Success | Menjadwalkan sesi training pelanggan | Agus Setiawan | High | In Progress | 21 | 2026-10-15 | 2026-11-23 | 24 | No | 2026-10-27 | Sedang dikerjakan
TASK-064 | Client Onboarding | Customer Success | Memantau SLA respons | Nadia Putri | Low | Not Started | 0 | 2026-09-18 | 2026-11-12 | 13 | No | 2026-10-27 | Belum dimulai; masuk backlog
TASK-065 | Learning & Development | Human Resources | Mengumpulkan feedback karyawan | Rafi Hidayat | High | In Review | 80 | 2026-09-05 | 2026-12-04 | 35 | No | 2026-10-29 | Menunggu review stakeholder
TASK-066 | Digital Marketing Optimization | Marketing & Communications | Menyiapkan materi media sosial | Kevin Hartono | Medium | In Progress | 72 | 2026-10-11 | 2026-11-07 | 8 | No | 2026-10-29 | Sesuai rencana kerja
TASK-067 | Budget Control Initiative | Finance & Procurement | Menyiapkan purchase request | Rafi Hidayat | High | In Review | 97 | 2026-09-01 | 2026-11-04 | 5 | No | 2026-10-24 | Perlu validasi akhir
TASK-068 | Performance Management | Human Resources | Menyusun rencana pelatihan | Dimas Saputra | High | In Progress | 34 | 2026-09-28 | 2026-10-26 | -4 | Yes | 2026-10-28 | Sesuai rencana kerja
TASK-069 | Corporate Communications | Marketing & Communications | Menganalisis performa kampanye | Putri Ananda | Low | Blocked | 43 | 2026-10-01 | 2026-11-04 | 5 | No | 2026-10-29 | Dependensi vendor belum selesai
TASK-070 | Brand Awareness Campaign | Marketing & Communications | Memperbarui landing page | Agus Setiawan | Medium | In Progress | 26 | 2026-09-16 | 2026-12-08 | 39 | No | 2026-10-30 | Sesuai rencana kerja
TASK-071 | Vendor Management | Finance & Procurement | Membandingkan penawaran vendor | Kevin Hartono | Medium | Completed | 92 | 2026-10-02 | 2026-10-24 | -6 | No | 2026-10-28 | Deliverable sudah diserahkan
TASK-072 | Enterprise Process Improvement | Project Management | Memperbarui risk register | Aldi Wijaya | Medium | Not Started | 0 | 2026-08-15 | 2026-12-10 | 41 | No | 2026-10-30 | Perlu konfirmasi ruang lingkup
TASK-073 | Platform Reliability | Product & Engineering | Mengembangkan API endpoint | Putri Ananda | High | Completed | 97 | 2026-09-08 | 2026-10-28 | -2 | No | 2026-10-27 | Dokumentasi telah diperbarui
TASK-074 | SOP Standardization | Operations | Menyelesaikan tiket internal | Putri Ananda | Medium | In Review | 98 | 2026-09-08 | 2026-11-14 | 15 | No | 2026-10-29 | Menunggu review stakeholder
TASK-075 | Digital Marketing Optimization | Marketing & Communications | Menganalisis performa kampanye | Andi Pratama | Medium | In Progress | 30 | 2026-08-11 | 2026-10-26 | -4 | Yes | 2026-10-23 | Sedang dikerjakan
TASK-076 | Customer Experience Program | Customer Success | Memantau tiket dukungan | Budi Santoso | Medium | In Review | 94 | 2026-08-30 | 2026-10-24 | -6 | Yes | 2026-10-27 | Draft siap ditinjau
TASK-077 | Vendor Management | Finance & Procurement | Menyusun laporan pengeluaran | Rizky Maulana | High | Not Started | 0 | 2026-08-26 | 2026-10-27 | -3 | Yes | 2026-10-28 | Belum dimulai; masuk backlog
TASK-078 | Business Intelligence Dashboard | Data & Analytics | Mengumpulkan kebutuhan data | Kevin Hartono | Medium | Blocked | 28 | 2026-09-09 | 2026-10-29 | -1 | Yes | 2026-10-23 | Menunggu data dari tim terkait
TASK-079 | Budget Control Initiative | Finance & Procurement | Memproses reimbursement | Tania Wibowo | Critical | In Progress | 15 | 2026-10-04 | 2026-11-29 | 30 | No | 2026-10-25 | Koordinasi lintas tim berlangsung
TASK-080 | Procurement Efficiency | Finance & Procurement | Memverifikasi invoice vendor | Aldi Wijaya | Medium | Completed | 100 | 2026-08-30 | 2026-10-25 | -5 | No | 2026-10-28 | Selesai sesuai rencana
TASK-081 | Client Onboarding | Customer Success | Menyusun rencana tindak lanjut akun | Budi Santoso | Medium | In Progress | 72 | 2026-09-26 | 2026-10-30 | 0 | No | 2026-10-25 | Sedang dikerjakan
TASK-082 | SOP Standardization | Operations | Melakukan inspeksi proses | Maya Anggraini | Medium | In Progress | 73 | 2026-08-14 | 2026-11-29 | 30 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-083 | PMO Transformation | Project Management | Memantau dependensi antar-workstream | Rafi Hidayat | Low | In Progress | 61 | 2026-09-10 | 2026-11-30 | 31 | No | 2026-10-23 | Sesuai rencana kerja
TASK-084 | Operational Excellence | Operations | Memperbarui SOP operasional | Siti Rahma | Medium | In Review | 94 | 2026-10-06 | 2026-12-01 | 32 | No | 2026-10-26 | Menunggu review stakeholder
TASK-085 | Internal Workflow Automation | Product & Engineering | Memperbaiki bug prioritas tinggi | Intan Permata | Medium | Not Started | 0 | 2026-10-02 | 2026-10-28 | -2 | Yes | 2026-10-28 | Perlu konfirmasi ruang lingkup
TASK-086 | Procurement Efficiency | Finance & Procurement | Meninjau kontrak vendor | Dewi Lestari | Low | Not Started | 0 | 2026-10-10 | 2026-10-24 | -6 | Yes | 2026-10-29 | Belum dimulai; masuk backlog
TASK-087 | Platform Reliability | Product & Engineering | Memperbarui dokumentasi teknis | Lia Maharani | Medium | In Review | 95 | 2026-09-07 | 2026-12-03 | 34 | No | 2026-10-23 | Menunggu review stakeholder
TASK-088 | Customer Portal Revamp | Product & Engineering | Melakukan regression testing | Dimas Saputra | Low | Completed | 89 | 2026-10-05 | 2026-11-30 | 31 | No | 2026-10-26 | Dokumentasi telah diperbarui
TASK-089 | Annual Planning | Project Management | Memperbarui risk register | Rizky Maulana | Low | In Review | 95 | 2026-09-08 | 2026-10-26 | -4 | Yes | 2026-10-23 | Perlu validasi akhir
TASK-090 | Performance Management | Human Resources | Menyusun rencana pelatihan | Intan Permata | High | In Progress | 34 | 2026-10-09 | 2026-11-02 | 3 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-091 | Brand Awareness Campaign | Marketing & Communications | Menyiapkan materi media sosial | Yoga Firmansyah | Low | In Progress | 58 | 2026-09-10 | 2026-11-20 | 21 | No | 2026-10-28 | Koordinasi lintas tim berlangsung
TASK-092 | Customer Experience Program | Customer Success | Menindaklanjuti permintaan pelanggan | Dewi Lestari | High | In Progress | 66 | 2026-10-04 | 2026-11-28 | 29 | No | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-093 | Enterprise Process Improvement | Project Management | Menyusun weekly status report | Putri Ananda | Low | In Progress | 53 | 2026-08-20 | 2026-11-24 | 25 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-094 | Sales Performance Analytics | Data & Analytics | Memperbarui pipeline data | Citra Amelia | Medium | Completed | 99 | 2026-10-08 | 2026-11-03 | 4 | No | 2026-10-29 | Selesai sesuai rencana
TASK-095 | Brand Awareness Campaign | Marketing & Communications | Memperbarui landing page | Kevin Hartono | Medium | Completed | 100 | 2026-08-12 | 2026-11-14 | 15 | No | 2026-10-26 | Selesai sesuai rencana
TASK-096 | Enterprise Process Improvement | Project Management | Menyusun project charter | Rafi Hidayat | Medium | In Progress | 41 | 2026-08-08 | 2026-11-18 | 19 | No | 2026-10-28 | Sedang dikerjakan
TASK-097 | Customer Portal Revamp | Product & Engineering | Mengembangkan API endpoint | Rizky Maulana | Medium | In Review | 98 | 2026-09-18 | 2026-12-05 | 36 | No | 2026-10-23 | Menunggu review stakeholder
TASK-098 | Budget Control Initiative | Finance & Procurement | Memperbarui cash-flow forecast | Nadia Putri | High | In Progress | 79 | 2026-08-02 | 2026-11-06 | 7 | No | 2026-10-23 | Sesuai rencana kerja
TASK-099 | Learning & Development | Human Resources | Menyusun laporan HR bulanan | Yoga Firmansyah | Medium | In Progress | 35 | 2026-09-24 | 2026-11-26 | 27 | No | 2026-10-29 | Sedang dikerjakan
TASK-100 | Corporate Communications | Marketing & Communications | Menyiapkan materi media sosial | Yoga Firmansyah | Medium | In Progress | 12 | 2026-09-15 | 2026-11-05 | 6 | No | 2026-10-30 | Sedang dikerjakan
TASK-101 | Annual Planning | Project Management | Menyiapkan laporan milestone | Putri Ananda | High | Completed | 100 | 2026-10-03 | 2026-11-08 | 9 | No | 2026-10-27 | Deliverable sudah diserahkan
TASK-102 | Digital Marketing Optimization | Marketing & Communications | Menyusun laporan komunikasi | Siti Rahma | Medium | Not Started | 0 | 2026-08-18 | 2026-11-22 | 23 | No | 2026-10-23 | Belum dimulai; masuk backlog
TASK-103 | Enterprise Process Improvement | Project Management | Menyiapkan laporan milestone | Fajar Nugroho | High | Completed | 100 | 2026-08-17 | 2026-11-06 | 7 | No | 2026-10-25 | Selesai sesuai rencana
TASK-104 | Budget Control Initiative | Finance & Procurement | Membandingkan penawaran vendor | Kevin Hartono | Low | In Progress | 24 | 2026-10-01 | 2026-12-09 | 40 | No | 2026-10-28 | Sesuai rencana kerja
TASK-105 | Corporate Communications | Marketing & Communications | Menyiapkan materi media sosial | Dewi Lestari | Critical | Blocked | 44 | 2026-09-16 | 2026-11-22 | 23 | No | 2026-10-25 | Dependensi vendor belum selesai
TASK-106 | Budget Control Initiative | Finance & Procurement | Menyusun laporan pengeluaran | Citra Amelia | Medium | In Review | 99 | 2026-09-17 | 2026-11-01 | 2 | No | 2026-10-27 | Perlu validasi akhir
TASK-107 | Sales Performance Analytics | Data & Analytics | Mendokumentasikan data dictionary | Maya Anggraini | High | In Progress | 14 | 2026-09-08 | 2026-11-28 | 29 | No | 2026-10-29 | Sedang dikerjakan
TASK-108 | Sales Performance Analytics | Data & Analytics | Menyusun definisi KPI | Tania Wibowo | Medium | In Progress | 79 | 2026-08-18 | 2026-11-05 | 6 | No | 2026-10-28 | Koordinasi lintas tim berlangsung
TASK-109 | SOP Standardization | Operations | Memeriksa checklist operasional | Kevin Hartono | High | Not Started | 0 | 2026-09-22 | 2026-11-25 | 26 | No | 2026-10-27 | Belum dimulai; masuk backlog
TASK-110 | Performance Management | Human Resources | Menjadwalkan wawancara kandidat | Agus Setiawan | Medium | Completed | 85 | 2026-09-17 | 2026-12-01 | 32 | No | 2026-10-29 | Selesai sesuai rencana
TASK-111 | Client Onboarding | Customer Success | Menganalisis feedback pelanggan | Dimas Saputra | Low | In Review | 81 | 2026-08-28 | 2026-12-11 | 42 | No | 2026-10-28 | Menunggu review stakeholder
TASK-112 | Corporate Communications | Marketing & Communications | Menulis draft artikel | Rizky Maulana | Low | In Progress | 52 | 2026-08-27 | 2026-11-26 | 27 | No | 2026-10-30 | Koordinasi lintas tim berlangsung
TASK-113 | Procurement Efficiency | Finance & Procurement | Membandingkan penawaran vendor | Andi Pratama | High | Blocked | 65 | 2026-10-09 | 2026-11-02 | 3 | No | 2026-10-30 | Menunggu data dari tim terkait
TASK-114 | Performance Management | Human Resources | Memperbarui database pelatihan | Rafi Hidayat | Critical | In Progress | 63 | 2026-09-11 | 2026-11-29 | 30 | No | 2026-10-29 | Sesuai rencana kerja
TASK-115 | Support Process Improvement | Customer Success | Memvalidasi penyelesaian keluhan | Putri Ananda | Medium | Not Started | 0 | 2026-10-05 | 2026-10-25 | -5 | Yes | 2026-10-26 | Menunggu prioritas sprint
TASK-116 | Customer Experience Program | Customer Success | Menindaklanjuti permintaan pelanggan | Kevin Hartono | Medium | In Progress | 72 | 2026-10-01 | 2026-10-22 | -8 | Yes | 2026-10-29 | Sesuai rencana kerja
TASK-117 | Talent Acquisition Sprint | Human Resources | Menyusun laporan HR bulanan | Dimas Saputra | Medium | In Progress | 80 | 2026-08-09 | 2026-12-05 | 36 | No | 2026-10-26 | Sedang dikerjakan
TASK-118 | Client Onboarding | Customer Success | Menyusun rencana tindak lanjut akun | Citra Amelia | High | Blocked | 51 | 2026-09-25 | 2026-12-06 | 37 | No | 2026-10-27 | Menunggu persetujuan manajer
TASK-119 | Operational Excellence | Operations | Menyelesaikan tiket internal | Dimas Saputra | Medium | Completed | 100 | 2026-09-22 | 2026-11-28 | 29 | No | 2026-10-25 | Deliverable sudah diserahkan
TASK-120 | Procurement Efficiency | Finance & Procurement | Melakukan rekonsiliasi biaya | Tania Wibowo | Critical | Not Started | 0 | 2026-09-30 | 2026-12-12 | 43 | No | 2026-10-25 | Menunggu prioritas sprint
TASK-121 | Customer Portal Revamp | Product & Engineering | Menyiapkan staging release | Rina Kurnia | Medium | In Review | 93 | 2026-10-15 | 2026-11-21 | 22 | No | 2026-10-24 | Draft siap ditinjau
TASK-122 | Annual Planning | Project Management | Memperbarui risk register | Rizky Maulana | Medium | Not Started | 0 | 2026-09-09 | 2026-11-19 | 20 | No | 2026-10-23 | Perlu konfirmasi ruang lingkup
TASK-123 | Digital Marketing Optimization | Marketing & Communications | Menulis draft artikel | Intan Permata | High | Not Started | 0 | 2026-10-11 | 2026-11-18 | 19 | No | 2026-10-30 | Belum dimulai; masuk backlog
TASK-124 | Procurement Efficiency | Finance & Procurement | Memverifikasi invoice vendor | Andi Pratama | Low | Blocked | 32 | 2026-09-04 | 2026-12-10 | 41 | No | 2026-10-28 | Menunggu data dari tim terkait
TASK-125 | Operational Excellence | Operations | Memeriksa checklist operasional | Kevin Hartono | High | Blocked | 36 | 2026-08-04 | 2026-11-10 | 11 | No | 2026-10-28 | Dependensi vendor belum selesai
TASK-126 | Performance Management | Human Resources | Mengumpulkan feedback karyawan | Rizky Maulana | Medium | Completed | 100 | 2026-09-11 | 2026-12-11 | 42 | No | 2026-10-30 | Selesai sesuai rencana
TASK-127 | Data Quality Initiative | Data & Analytics | Membangun dashboard monitoring | Rafi Hidayat | Medium | In Review | 86 | 2026-09-24 | 2026-11-06 | 7 | No | 2026-10-25 | Menunggu review stakeholder
TASK-128 | SOP Standardization | Operations | Memeriksa checklist operasional | Yoga Firmansyah | High | In Progress | 38 | 2026-10-15 | 2026-10-22 | -8 | Yes | 2026-10-30 | Koordinasi lintas tim berlangsung
TASK-129 | Enterprise Process Improvement | Project Management | Mengidentifikasi risiko proyek | Dewi Lestari | High | In Progress | 51 | 2026-08-28 | 2026-11-13 | 14 | No | 2026-10-23 | Sesuai rencana kerja
TASK-130 | Operational Excellence | Operations | Menindaklanjuti temuan audit | Budi Santoso | Medium | In Review | 91 | 2026-09-18 | 2026-12-12 | 43 | No | 2026-10-30 | Perlu validasi akhir
TASK-131 | SOP Standardization | Operations | Memperbarui SOP operasional | Tania Wibowo | Medium | In Progress | 61 | 2026-08-10 | 2026-11-07 | 8 | No | 2026-10-29 | Sedang dikerjakan
TASK-132 | SOP Standardization | Operations | Memperbarui SOP operasional | Budi Santoso | Medium | Completed | 100 | 2026-08-22 | 2026-12-03 | 34 | No | 2026-10-29 | Deliverable sudah diserahkan
TASK-133 | Corporate Communications | Marketing & Communications | Menyiapkan materi media sosial | Dimas Saputra | Low | Not Started | 0 | 2026-09-21 | 2026-12-12 | 43 | No | 2026-10-25 | Menunggu prioritas sprint
TASK-134 | Platform Reliability | Product & Engineering | Membuat wireframe fitur | Rina Kurnia | Low | In Progress | 54 | 2026-08-15 | 2026-12-11 | 42 | No | 2026-10-28 | Koordinasi lintas tim berlangsung
TASK-135 | Brand Awareness Campaign | Marketing & Communications | Menulis draft artikel | Nadia Putri | High | In Progress | 19 | 2026-09-02 | 2026-12-07 | 38 | No | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-136 | Client Onboarding | Customer Success | Memantau SLA respons | Dimas Saputra | Medium | Completed | 100 | 2026-09-27 | 2026-10-21 | -9 | No | 2026-10-23 | Selesai sesuai rencana
TASK-137 | Data Quality Initiative | Data & Analytics | Mendokumentasikan data dictionary | Budi Santoso | Critical | In Progress | 74 | 2026-09-08 | 2026-11-16 | 17 | No | 2026-10-23 | Sedang dikerjakan
TASK-138 | Customer Experience Program | Customer Success | Menindaklanjuti permintaan pelanggan | Putri Ananda | Medium | In Progress | 21 | 2026-09-17 | 2026-11-29 | 30 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-139 | Client Onboarding | Customer Success | Memantau SLA respons | Putri Ananda | Medium | Completed | 100 | 2026-08-06 | 2026-10-23 | -7 | No | 2026-10-28 | Deliverable sudah diserahkan
TASK-140 | PMO Transformation | Project Management | Memantau dependensi antar-workstream | Siti Rahma | Medium | Not Started | 0 | 2026-09-13 | 2026-12-08 | 39 | No | 2026-10-23 | Menunggu prioritas sprint
TASK-141 | Client Onboarding | Customer Success | Menyusun rencana tindak lanjut akun | Dimas Saputra | High | In Progress | 62 | 2026-08-21 | 2026-11-09 | 10 | No | 2026-10-30 | Koordinasi lintas tim berlangsung
TASK-142 | Learning & Development | Human Resources | Menjadwalkan wawancara kandidat | Rizky Maulana | High | In Review | 99 | 2026-08-13 | 2026-10-28 | -2 | Yes | 2026-10-29 | Perlu validasi akhir
TASK-143 | Internal Workflow Automation | Product & Engineering | Menulis unit test | Citra Amelia | Low | In Review | 89 | 2026-09-20 | 2026-12-04 | 35 | No | 2026-10-25 | Perlu validasi akhir
TASK-144 | Customer Portal Revamp | Product & Engineering | Menyiapkan staging release | Fajar Nugroho | High | In Progress | 33 | 2026-09-24 | 2026-11-01 | 2 | No | 2026-10-23 | Sedang dikerjakan
TASK-145 | Brand Awareness Campaign | Marketing & Communications | Menganalisis performa kampanye | Citra Amelia | Medium | In Progress | 74 | 2026-08-20 | 2026-11-13 | 14 | No | 2026-10-30 | Koordinasi lintas tim berlangsung
TASK-146 | Talent Acquisition Sprint | Human Resources | Menyusun laporan HR bulanan | Kevin Hartono | Medium | In Progress | 31 | 2026-09-18 | 2026-10-30 | 0 | No | 2026-10-24 | Sesuai rencana kerja
TASK-147 | Learning & Development | Human Resources | Memperbarui database pelatihan | Intan Permata | Medium | Blocked | 44 | 2026-09-06 | 2026-11-29 | 30 | No | 2026-10-23 | Dependensi vendor belum selesai
TASK-148 | Corporate Communications | Marketing & Communications | Menyusun newsletter | Rafi Hidayat | High | In Progress | 58 | 2026-10-13 | 2026-11-04 | 5 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-149 | Platform Reliability | Product & Engineering | Melakukan code review | Citra Amelia | Medium | In Progress | 57 | 2026-08-18 | 2026-10-28 | -2 | Yes | 2026-10-29 | Sesuai rencana kerja
TASK-150 | Procurement Efficiency | Finance & Procurement | Memperbarui tracking anggaran | Intan Permata | High | Completed | 100 | 2026-09-04 | 2026-11-01 | 2 | No | 2026-10-25 | Deliverable sudah diserahkan
TASK-151 | PMO Transformation | Project Management | Mencatat keputusan rapat | Rina Kurnia | Medium | In Progress | 20 | 2026-09-20 | 2026-10-25 | -5 | Yes | 2026-10-30 | Sesuai rencana kerja
TASK-152 | Performance Management | Human Resources | Menjadwalkan wawancara kandidat | Rizky Maulana | Critical | In Progress | 70 | 2026-09-12 | 2026-12-07 | 38 | No | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-153 | Customer Experience Program | Customer Success | Memantau SLA respons | Putri Ananda | Medium | In Progress | 80 | 2026-08-11 | 2026-12-06 | 37 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-154 | Business Intelligence Dashboard | Data & Analytics | Membangun dashboard monitoring | Putri Ananda | Medium | Not Started | 0 | 2026-09-08 | 2026-11-08 | 9 | No | 2026-10-29 | Belum dimulai; masuk backlog
TASK-155 | Sales Performance Analytics | Data & Analytics | Mendokumentasikan data dictionary | Maya Anggraini | Medium | In Review | 84 | 2026-10-08 | 2026-11-15 | 16 | No | 2026-10-30 | Perlu validasi akhir
TASK-156 | Performance Management | Human Resources | Memperbarui database pelatihan | Budi Santoso | Critical | In Review | 91 | 2026-09-23 | 2026-11-30 | 31 | No | 2026-10-30 | Draft siap ditinjau
TASK-157 | Operational Excellence | Operations | Menyelesaikan tiket internal | Rina Kurnia | Critical | In Progress | 18 | 2026-09-19 | 2026-12-07 | 38 | No | 2026-10-29 | Sesuai rencana kerja
TASK-158 | Talent Acquisition Sprint | Human Resources | Menyiapkan onboarding karyawan | Lia Maharani | Medium | In Progress | 69 | 2026-09-15 | 2026-12-02 | 33 | No | 2026-10-28 | Koordinasi lintas tim berlangsung
TASK-159 | Platform Reliability | Product & Engineering | Membuat wireframe fitur | Siti Rahma | Critical | In Progress | 35 | 2026-09-28 | 2026-11-25 | 26 | No | 2026-10-26 | Sedang dikerjakan
TASK-160 | SOP Standardization | Operations | Mengidentifikasi bottleneck proses | Siti Rahma | High | Blocked | 32 | 2026-09-02 | 2026-11-12 | 13 | No | 2026-10-25 | Menunggu persetujuan manajer
TASK-161 | Budget Control Initiative | Finance & Procurement | Memperbarui tracking anggaran | Dimas Saputra | Low | Blocked | 34 | 2026-09-25 | 2026-10-24 | -6 | Yes | 2026-10-23 | Menunggu data dari tim terkait
TASK-162 | Client Onboarding | Customer Success | Menyusun panduan pengguna | Tania Wibowo | Medium | Not Started | 0 | 2026-09-04 | 2026-11-20 | 21 | No | 2026-10-28 | Perlu konfirmasi ruang lingkup
TASK-163 | Procurement Efficiency | Finance & Procurement | Melakukan rekonsiliasi biaya | Tania Wibowo | High | In Review | 99 | 2026-08-11 | 2026-12-06 | 37 | No | 2026-10-23 | Menunggu review stakeholder
TASK-164 | Talent Acquisition Sprint | Human Resources | Memantau target rekrutmen | Budi Santoso | High | Completed | 100 | 2026-09-15 | 2026-11-07 | 8 | No | 2026-10-24 | Dokumentasi telah diperbarui
TASK-165 | Performance Management | Human Resources | Menyiapkan evaluasi kinerja | Siti Rahma | Medium | In Progress | 66 | 2026-08-21 | 2026-11-30 | 31 | No | 2026-10-29 | Sesuai rencana kerja
TASK-166 | Digital Marketing Optimization | Marketing & Communications | Menyusun newsletter | Kevin Hartono | High | Not Started | 0 | 2026-09-19 | 2026-11-06 | 7 | No | 2026-10-25 | Belum dimulai; masuk backlog
TASK-167 | Client Onboarding | Customer Success | Menganalisis feedback pelanggan | Intan Permata | High | In Progress | 45 | 2026-08-18 | 2026-11-07 | 8 | No | 2026-10-30 | Sesuai rencana kerja
TASK-168 | Platform Reliability | Product & Engineering | Memperbarui dokumentasi teknis | Kevin Hartono | Medium | Not Started | 0 | 2026-09-19 | 2026-11-05 | 6 | No | 2026-10-26 | Menunggu prioritas sprint
TASK-169 | Customer Experience Program | Customer Success | Menyiapkan laporan kepuasan pelanggan | Kevin Hartono | High | Not Started | 0 | 2026-08-18 | 2026-10-27 | -3 | Yes | 2026-10-25 | Menunggu prioritas sprint
TASK-170 | Performance Management | Human Resources | Menjadwalkan wawancara kandidat | Rina Kurnia | Low | Completed | 100 | 2026-10-09 | 2026-11-22 | 23 | No | 2026-10-27 | Dokumentasi telah diperbarui
TASK-171 | Business Intelligence Dashboard | Data & Analytics | Menyusun definisi KPI | Rina Kurnia | High | In Progress | 83 | 2026-08-31 | 2026-12-11 | 42 | No | 2026-10-28 | Sedang dikerjakan
TASK-172 | Data Quality Initiative | Data & Analytics | Membersihkan dataset operasional | Aldi Wijaya | Medium | In Review | 93 | 2026-09-20 | 2026-11-04 | 5 | No | 2026-10-28 | Menunggu review stakeholder
TASK-173 | Learning & Development | Human Resources | Menjadwalkan wawancara kandidat | Aldi Wijaya | High | In Progress | 80 | 2026-09-29 | 2026-11-07 | 8 | No | 2026-10-28 | Sesuai rencana kerja
TASK-174 | Operational Excellence | Operations | Mengidentifikasi bottleneck proses | Intan Permata | High | In Progress | 51 | 2026-08-16 | 2026-11-03 | 4 | No | 2026-10-26 | Sedang dikerjakan
TASK-175 | Business Intelligence Dashboard | Data & Analytics | Membangun dashboard monitoring | Citra Amelia | High | Not Started | 0 | 2026-10-10 | 2026-11-21 | 22 | No | 2026-10-28 | Menunggu prioritas sprint
TASK-176 | Platform Reliability | Product & Engineering | Mengembangkan API endpoint | Budi Santoso | Critical | Completed | 100 | 2026-09-13 | 2026-11-09 | 10 | No | 2026-10-26 | Selesai sesuai rencana
TASK-177 | Digital Marketing Optimization | Marketing & Communications | Menyusun laporan komunikasi | Lia Maharani | Medium | Completed | 100 | 2026-08-04 | 2026-12-01 | 32 | No | 2026-10-24 | Selesai sesuai rencana
TASK-178 | Procurement Efficiency | Finance & Procurement | Memperbarui cash-flow forecast | Dimas Saputra | Medium | In Progress | 36 | 2026-08-08 | 2026-10-22 | -8 | Yes | 2026-10-28 | Koordinasi lintas tim berlangsung
TASK-179 | Performance Management | Human Resources | Menyusun rencana pelatihan | Dewi Lestari | High | In Progress | 81 | 2026-09-14 | 2026-11-07 | 8 | No | 2026-10-27 | Sedang dikerjakan
TASK-180 | Support Process Improvement | Customer Success | Menganalisis feedback pelanggan | Putri Ananda | Critical | In Progress | 59 | 2026-09-27 | 2026-11-19 | 20 | No | 2026-10-27 | Sedang dikerjakan
TASK-181 | Platform Reliability | Product & Engineering | Menulis unit test | Kevin Hartono | Medium | Blocked | 42 | 2026-09-10 | 2026-11-28 | 29 | No | 2026-10-26 | Dependensi vendor belum selesai
TASK-182 | Customer Experience Program | Customer Success | Menindaklanjuti permintaan pelanggan | Rina Kurnia | High | In Progress | 84 | 2026-09-20 | 2026-10-28 | -2 | Yes | 2026-10-30 | Sesuai rencana kerja
TASK-183 | Vendor Management | Finance & Procurement | Memperbarui cash-flow forecast | Rizky Maulana | Medium | In Progress | 65 | 2026-09-30 | 2026-11-09 | 10 | No | 2026-10-25 | Sedang dikerjakan
TASK-184 | Operational Excellence | Operations | Melakukan inspeksi proses | Maya Anggraini | High | In Review | 97 | 2026-09-21 | 2026-11-18 | 19 | No | 2026-10-24 | Menunggu review stakeholder
TASK-185 | Support Process Improvement | Customer Success | Menyusun rencana tindak lanjut akun | Citra Amelia | Medium | Completed | 100 | 2026-08-16 | 2026-11-05 | 6 | No | 2026-10-28 | Deliverable sudah diserahkan
TASK-186 | Corporate Communications | Marketing & Communications | Menyusun laporan komunikasi | Dimas Saputra | Critical | Not Started | 0 | 2026-09-21 | 2026-10-31 | 1 | No | 2026-10-23 | Belum dimulai; masuk backlog
TASK-187 | Platform Reliability | Product & Engineering | Melakukan deployment ke production | Aldi Wijaya | High | Completed | 100 | 2026-08-18 | 2026-11-18 | 19 | No | 2026-10-23 | Deliverable sudah diserahkan
TASK-188 | Procurement Efficiency | Finance & Procurement | Memperbarui cash-flow forecast | Maya Anggraini | Low | In Review | 98 | 2026-09-17 | 2026-10-23 | -7 | Yes | 2026-10-30 | Draft siap ditinjau
TASK-189 | Client Onboarding | Customer Success | Memantau tiket dukungan | Nadia Putri | Critical | In Progress | 71 | 2026-10-14 | 2026-11-24 | 25 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-190 | Customer Portal Revamp | Product & Engineering | Melakukan code review | Dimas Saputra | Critical | Not Started | 0 | 2026-10-13 | 2026-11-12 | 13 | No | 2026-10-28 | Belum dimulai; masuk backlog
TASK-191 | SOP Standardization | Operations | Memantau SLA layanan | Rizky Maulana | Medium | In Review | 81 | 2026-10-04 | 2026-10-22 | -8 | Yes | 2026-10-27 | Draft siap ditinjau
TASK-192 | Performance Management | Human Resources | Memantau target rekrutmen | Citra Amelia | Medium | Completed | 100 | 2026-09-18 | 2026-11-23 | 24 | No | 2026-10-26 | Deliverable sudah diserahkan
TASK-193 | Customer Experience Program | Customer Success | Menyiapkan laporan kepuasan pelanggan | Maya Anggraini | Low | In Progress | 48 | 2026-09-05 | 2026-12-07 | 38 | No | 2026-10-27 | Koordinasi lintas tim berlangsung
TASK-194 | Support Process Improvement | Customer Success | Menyusun panduan pengguna | Dewi Lestari | Medium | Completed | 100 | 2026-09-14 | 2026-11-07 | 8 | No | 2026-10-24 | Dokumentasi telah diperbarui
TASK-195 | Operational Excellence | Operations | Melakukan inspeksi proses | Kevin Hartono | Medium | In Progress | 54 | 2026-09-07 | 2026-11-04 | 5 | No | 2026-10-26 | Koordinasi lintas tim berlangsung
TASK-196 | Customer Experience Program | Customer Success | Menyiapkan laporan kepuasan pelanggan | Putri Ananda | Medium | Completed | 100 | 2026-10-08 | 2026-11-12 | 13 | No | 2026-10-27 | Dokumentasi telah diperbarui
TASK-197 | Corporate Communications | Marketing & Communications | Menyusun kalender konten | Dimas Saputra | Critical | In Review | 93 | 2026-10-07 | 2026-11-04 | 5 | No | 2026-10-23 | Draft siap ditinjau
TASK-198 | Business Intelligence Dashboard | Data & Analytics | Memvalidasi kualitas data | Lia Maharani | Low | In Progress | 70 | 2026-10-10 | 2026-12-08 | 39 | No | 2026-10-27 | Koordinasi lintas tim berlangsung
TASK-199 | Budget Control Initiative | Finance & Procurement | Melakukan rekonsiliasi biaya | Citra Amelia | Medium | Not Started | 0 | 2026-08-08 | 2026-11-28 | 29 | No | 2026-10-30 | Perlu konfirmasi ruang lingkup
TASK-200 | Customer Portal Revamp | Product & Engineering | Melakukan regression testing | Siti Rahma | Medium | In Progress | 47 | 2026-08-05 | 2026-12-04 | 35 | No | 2026-10-26 | Sesuai rencana kerja
TASK-201 | Data Quality Initiative | Data & Analytics | Memperbarui pipeline data | Rafi Hidayat | Medium | In Progress | 27 | 2026-09-28 | 2026-11-04 | 5 | No | 2026-10-26 | Sedang dikerjakan
TASK-202 | Digital Marketing Optimization | Marketing & Communications | Menulis draft artikel | Andi Pratama | High | In Progress | 33 | 2026-08-21 | 2026-10-30 | 0 | No | 2026-10-25 | Koordinasi lintas tim berlangsung
TASK-203 | Vendor Management | Finance & Procurement | Menyusun laporan pengeluaran | Tania Wibowo | Medium | In Review | 92 | 2026-08-25 | 2026-11-29 | 30 | No | 2026-10-25 | Draft siap ditinjau
TASK-204 | Sales Performance Analytics | Data & Analytics | Menganalisis tren kinerja | Andi Pratama | Medium | Completed | 100 | 2026-08-13 | 2026-10-30 | 0 | No | 2026-10-24 | Deliverable sudah diserahkan
TASK-205 | Digital Marketing Optimization | Marketing & Communications | Melakukan riset audiens | Rina Kurnia | Medium | In Review | 88 | 2026-09-12 | 2026-11-29 | 30 | No | 2026-10-27 | Draft siap ditinjau
TASK-206 | Enterprise Process Improvement | Project Management | Memperbarui project timeline | Dewi Lestari | Medium | In Progress | 49 | 2026-09-09 | 2026-12-10 | 41 | No | 2026-10-26 | Koordinasi lintas tim berlangsung
TASK-207 | Talent Acquisition Sprint | Human Resources | Menyusun laporan HR bulanan | Tania Wibowo | Medium | In Progress | 57 | 2026-08-29 | 2026-10-28 | -2 | Yes | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-208 | Corporate Communications | Marketing & Communications | Menganalisis performa kampanye | Aldi Wijaya | Medium | In Progress | 19 | 2026-08-11 | 2026-11-20 | 21 | No | 2026-10-30 | Sesuai rencana kerja
TASK-209 | Corporate Communications | Marketing & Communications | Menyusun laporan komunikasi | Fajar Nugroho | Medium | In Progress | 24 | 2026-08-20 | 2026-11-24 | 25 | No | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-210 | Data Quality Initiative | Data & Analytics | Melakukan rekonsiliasi data | Siti Rahma | Medium | In Progress | 82 | 2026-08-08 | 2026-11-03 | 4 | No | 2026-10-23 | Koordinasi lintas tim berlangsung
TASK-211 | Budget Control Initiative | Finance & Procurement | Memverifikasi invoice vendor | Budi Santoso | High | Not Started | 0 | 2026-09-02 | 2026-12-03 | 34 | No | 2026-10-24 | Menunggu prioritas sprint
TASK-212 | Performance Management | Human Resources | Menjadwalkan wawancara kandidat | Nadia Putri | Medium | Completed | 89 | 2026-08-08 | 2026-11-16 | 17 | No | 2026-10-24 | Selesai sesuai rencana
TASK-213 | Learning & Development | Human Resources | Memeriksa kelengkapan dokumen HR | Citra Amelia | Low | Not Started | 0 | 2026-09-18 | 2026-12-05 | 36 | No | 2026-10-25 | Menunggu prioritas sprint
TASK-214 | Sales Performance Analytics | Data & Analytics | Memvalidasi kualitas data | Andi Pratama | Low | Not Started | 0 | 2026-09-20 | 2026-12-02 | 33 | No | 2026-10-26 | Menunggu prioritas sprint
TASK-215 | Support Process Improvement | Customer Success | Menyusun rencana tindak lanjut akun | Agus Setiawan | High | Completed | 100 | 2026-10-08 | 2026-11-27 | 28 | No | 2026-10-29 | Selesai sesuai rencana
TASK-216 | Annual Planning | Project Management | Mencatat keputusan rapat | Kevin Hartono | High | In Progress | 14 | 2026-08-03 | 2026-11-01 | 2 | No | 2026-10-30 | Koordinasi lintas tim berlangsung
TASK-217 | Digital Marketing Optimization | Marketing & Communications | Menyusun kalender konten | Rizky Maulana | Medium | In Progress | 17 | 2026-09-26 | 2026-11-28 | 29 | No | 2026-10-26 | Koordinasi lintas tim berlangsung
TASK-218 | Digital Marketing Optimization | Marketing & Communications | Menyusun laporan komunikasi | Maya Anggraini | Medium | Blocked | 25 | 2026-10-13 | 2026-11-25 | 26 | No | 2026-10-27 | Menunggu data dari tim terkait
TASK-219 | SOP Standardization | Operations | Mengatur jadwal operasional | Tania Wibowo | Low | Completed | 100 | 2026-08-08 | 2026-11-10 | 11 | No | 2026-10-23 | Dokumentasi telah diperbarui
TASK-220 | Annual Planning | Project Management | Menyiapkan rapat steering committee | Rizky Maulana | Medium | In Progress | 62 | 2026-09-18 | 2026-11-02 | 3 | No | 2026-10-24 | Sedang dikerjakan
TASK-221 | Internal Workflow Automation | Product & Engineering | Menyiapkan staging release | Kevin Hartono | Low | In Progress | 28 | 2026-08-31 | 2026-12-06 | 37 | No | 2026-10-24 | Sesuai rencana kerja
TASK-222 | Service Delivery Improvement | Operations | Mengidentifikasi bottleneck proses | Kevin Hartono | High | In Progress | 20 | 2026-08-18 | 2026-11-21 | 22 | No | 2026-10-29 | Sedang dikerjakan
TASK-223 | Digital Marketing Optimization | Marketing & Communications | Menyusun kalender konten | Fajar Nugroho | Critical | In Review | 82 | 2026-09-18 | 2026-12-10 | 41 | No | 2026-10-27 | Draft siap ditinjau
TASK-224 | Support Process Improvement | Customer Success | Menyiapkan laporan kepuasan pelanggan | Lia Maharani | High | In Progress | 25 | 2026-09-08 | 2026-11-06 | 7 | No | 2026-10-27 | Sesuai rencana kerja
TASK-225 | Service Delivery Improvement | Operations | Memantau SLA layanan | Maya Anggraini | Medium | In Progress | 55 | 2026-09-11 | 2026-12-12 | 43 | No | 2026-10-25 | Sedang dikerjakan
TASK-226 | Customer Experience Program | Customer Success | Memvalidasi penyelesaian keluhan | Tania Wibowo | Low | Completed | 100 | 2026-09-30 | 2026-10-30 | 0 | No | 2026-10-27 | Selesai sesuai rencana
TASK-227 | Internal Workflow Automation | Product & Engineering | Menyusun user story | Fajar Nugroho | Medium | In Review | 84 | 2026-10-10 | 2026-12-07 | 38 | No | 2026-10-27 | Perlu validasi akhir
TASK-228 | Operational Excellence | Operations | Menyusun laporan operasional | Lia Maharani | Medium | In Review | 88 | 2026-10-03 | 2026-10-21 | -9 | Yes | 2026-10-23 | Draft siap ditinjau
TASK-229 | Client Onboarding | Customer Success | Memperbarui knowledge base | Citra Amelia | Medium | In Progress | 33 | 2026-09-15 | 2026-11-15 | 16 | No | 2026-10-30 | Koordinasi lintas tim berlangsung
TASK-230 | Annual Planning | Project Management | Memperbarui project timeline | Intan Permata | High | Not Started | 0 | 2026-08-07 | 2026-10-23 | -7 | Yes | 2026-10-28 | Menunggu prioritas sprint
TASK-231 | Annual Planning | Project Management | Mengidentifikasi risiko proyek | Putri Ananda | Medium | Not Started | 0 | 2026-09-28 | 2026-10-30 | 0 | No | 2026-10-23 | Belum dimulai; masuk backlog
TASK-232 | Annual Planning | Project Management | Menyusun project charter | Agus Setiawan | Medium | Not Started | 0 | 2026-10-10 | 2026-12-04 | 35 | No | 2026-10-26 | Perlu konfirmasi ruang lingkup
TASK-233 | Annual Planning | Project Management | Memvalidasi scope pekerjaan | Rafi Hidayat | High | Completed | 100 | 2026-09-25 | 2026-11-04 | 5 | No | 2026-10-27 | Selesai sesuai rencana
TASK-234 | Corporate Communications | Marketing & Communications | Menyusun laporan komunikasi | Rina Kurnia | Medium | In Progress | 20 | 2026-09-02 | 2026-12-04 | 35 | No | 2026-10-23 | Sedang dikerjakan
TASK-235 | Digital Marketing Optimization | Marketing & Communications | Menganalisis performa kampanye | Yoga Firmansyah | Medium | Completed | 100 | 2026-08-11 | 2026-11-19 | 20 | No | 2026-10-24 | Deliverable sudah diserahkan
TASK-236 | Client Onboarding | Customer Success | Menindaklanjuti permintaan pelanggan | Dimas Saputra | Medium | In Progress | 65 | 2026-08-02 | 2026-12-12 | 43 | No | 2026-10-29 | Koordinasi lintas tim berlangsung
TASK-237 | PMO Transformation | Project Management | Mengidentifikasi risiko proyek | Citra Amelia | Low | In Progress | 45 | 2026-10-12 | 2026-11-30 | 31 | No | 2026-10-30 | Koordinasi lintas tim berlangsung
TASK-238 | Customer Portal Revamp | Product & Engineering | Menulis unit test | Budi Santoso | Medium | In Progress | 60 | 2026-08-27 | 2026-12-02 | 33 | No | 2026-10-28 | Sedang dikerjakan
TASK-239 | Digital Marketing Optimization | Marketing & Communications | Menyusun laporan komunikasi | Rafi Hidayat | Medium | In Progress | 20 | 2026-10-09 | 2026-11-25 | 26 | No | 2026-10-25 | Koordinasi lintas tim berlangsung
TASK-240 | Enterprise Process Improvement | Project Management | Memperbarui project timeline | Putri Ananda | Medium | Not Started | 0 | 2026-08-30 | 2026-10-24 | -6 | Yes | 2026-10-24 | Perlu konfirmasi ruang lingkup
TASK-241 | Performance Management | Human Resources | Memperbarui manpower plan | Tania Wibowo | Medium | Completed | 90 | 2026-09-04 | 2026-11-06 | 7 | No | 2026-10-24 | Selesai sesuai rencana
TASK-242 | Data Quality Initiative | Data & Analytics | Menyusun insight untuk manajemen | Yoga Firmansyah | High | Not Started | 0 | 2026-09-01 | 2026-11-07 | 8 | No | 2026-10-28 | Perlu konfirmasi ruang lingkup
TASK-243 | SOP Standardization | Operations | Melakukan inspeksi proses | Rina Kurnia | High | Not Started | 0 | 2026-08-14 | 2026-11-22 | 23 | No | 2026-10-29 | Belum dimulai; masuk backlog
TASK-244 | Customer Portal Revamp | Product & Engineering | Membuat wireframe fitur | Andi Pratama | Medium | In Progress | 23 | 2026-09-25 | 2026-12-11 | 42 | No | 2026-10-25 | Sesuai rencana kerja
TASK-245 | Sales Performance Analytics | Data & Analytics | Menyusun insight untuk manajemen | Budi Santoso | High | In Progress | 59 | 2026-09-11 | 2026-11-11 | 12 | No | 2026-10-27 | Koordinasi lintas tim berlangsung
TASK-246 | Customer Portal Revamp | Product & Engineering | Melakukan regression testing | Nadia Putri | Medium | In Progress | 18 | 2026-08-18 | 2026-10-20 | -10 | Yes | 2026-10-26 | Sedang dikerjakan
TASK-247 | SOP Standardization | Operations | Mengatur jadwal operasional | Putri Ananda | High | In Progress | 73 | 2026-08-10 | 2026-11-03 | 4 | No | 2026-10-27 | Koordinasi lintas tim berlangsung
TASK-248 | Customer Experience Program | Customer Success | Menganalisis feedback pelanggan | Dimas Saputra | High | Completed | 94 | 2026-09-08 | 2026-10-24 | -6 | No | 2026-10-25 | Deliverable sudah diserahkan
TASK-249 | Operational Excellence | Operations | Menyusun laporan operasional | Dimas Saputra | Medium | In Review | 95 | 2026-09-08 | 2026-11-19 | 20 | No | 2026-10-24 | Menunggu review stakeholder
TASK-250 | Performance Management | Human Resources | Mengumpulkan feedback karyawan | Yoga Firmansyah | High | Blocked | 27 | 2026-10-02 | 2026-11-28 | 29 | No | 2026-10-29 | Dependensi vendor belum selesai
TASK-251 | Corporate Communications | Marketing & Communications | Menyusun laporan komunikasi | Kevin Hartono | Critical | Blocked | 56 | 2026-08-24 | 2026-11-18 | 19 | No | 2026-10-27 | Menunggu persetujuan manajer
TASK-252 | Client Onboarding | Customer Success | Memantau tiket dukungan | Rizky Maulana | Medium | Completed | 95 | 2026-08-09 | 2026-11-18 | 19 | No | 2026-10-26 | Dokumentasi telah diperbarui
TASK-253 | Corporate Communications | Marketing & Communications | Memperbarui landing page | Putri Ananda | High | In Progress | 67 | 2026-08-20 | 2026-10-28 | -2 | Yes | 2026-10-24 | Sedang dikerjakan
TASK-254 | Operational Excellence | Operations | Mengidentifikasi bottleneck proses | Dewi Lestari | Medium | Completed | 100 | 2026-09-16 | 2026-10-20 | -10 | No | 2026-10-25 | Selesai sesuai rencana
TASK-255 | Customer Portal Revamp | Product & Engineering | Melakukan deployment ke production | Tania Wibowo | Medium | In Review | 90 | 2026-10-12 | 2026-12-07 | 38 | No | 2026-10-30 | Menunggu review stakeholder
TASK-256 | Business Intelligence Dashboard | Data & Analytics | Membangun dashboard monitoring | Intan Permata | Medium | In Progress | 83 | 2026-10-05 | 2026-11-12 | 13 | No | 2026-10-25 | Sedang dikerjakan
TASK-257 | Service Delivery Improvement | Operations | Menyelesaikan tiket internal | Lia Maharani | High | In Progress | 13 | 2026-10-15 | 2026-11-28 | 29 | No | 2026-10-26 | Sesuai rencana kerja
TASK-258 | Operational Excellence | Operations | Memeriksa checklist operasional | Rafi Hidayat | Medium | In Progress | 36 | 2026-08-19 | 2026-12-04 | 35 | No | 2026-10-25 | Sedang dikerjakan
TASK-259 | Support Process Improvement | Customer Success | Menganalisis feedback pelanggan | Dewi Lestari | Critical | Not Started | 0 | 2026-09-27 | 2026-11-04 | 5 | No | 2026-10-25 | Menunggu prioritas sprint
TASK-260 | Sales Performance Analytics | Data & Analytics | Memvalidasi kualitas data | Tania Wibowo | High | In Progress | 81 | 2026-09-01 | 2026-11-01 | 2 | No | 2026-10-27 | Sedang dikerjakan
TASK-261 | Operational Excellence | Operations | Menindaklanjuti temuan audit | Fajar Nugroho | Medium | Not Started | 0 | 2026-09-25 | 2026-12-10 | 41 | No | 2026-10-24 | Belum dimulai; masuk backlog
TASK-262 | Service Delivery Improvement | Operations | Memperbarui SOP operasional | Aldi Wijaya | Medium | In Progress | 18 | 2026-08-28 | 2026-12-03 | 34 | No | 2026-10-28 | Sesuai rencana kerja
TASK-263 | Talent Acquisition Sprint | Human Resources | Menyusun rencana pelatihan | Dimas Saputra | Low | In Progress | 77 | 2026-09-28 | 2026-11-16 | 17 | No | 2026-10-24 | Koordinasi lintas tim berlangsung
TASK-264 | Operational Excellence | Operations | Menyusun laporan operasional | Putri Ananda | Medium | Completed | 100 | 2026-09-14 | 2026-10-23 | -7 | No | 2026-10-29 | Dokumentasi telah diperbarui
TASK-265 | Customer Portal Revamp | Product & Engineering | Menulis unit test | Rizky Maulana | High | Not Started | 0 | 2026-08-31 | 2026-11-06 | 7 | No | 2026-10-24 | Perlu konfirmasi ruang lingkup
TASK-266 | Operational Excellence | Operations | Menyusun laporan operasional | Nadia Putri | Medium | In Progress | 78 | 2026-10-13 | 2026-11-25 | 26 | No | 2026-10-28 | Koordinasi lintas tim berlangsung
TASK-267 | Customer Experience Program | Customer Success | Memantau tiket dukungan | Andi Pratama | Medium | Completed | 100 | 2026-08-24 | 2026-11-10 | 11 | No | 2026-10-28 | Deliverable sudah diserahkan
TASK-268 | Corporate Communications | Marketing & Communications | Menyiapkan materi media sosial | Kevin Hartono | Medium | In Progress | 63 | 2026-10-04 | 2026-10-22 | -8 | Yes | 2026-10-28 | Sedang dikerjakan
TASK-269 | Business Intelligence Dashboard | Data & Analytics | Menyusun insight untuk manajemen | Maya Anggraini | High | Not Started | 0 | 2026-08-29 | 2026-10-20 | -10 | Yes | 2026-10-23 | Menunggu prioritas sprint
TASK-270 | Client Onboarding | Customer Success | Menyusun rencana tindak lanjut akun | Rina Kurnia | Medium | Not Started | 0 | 2026-08-15 | 2026-11-15 | 16 | No | 2026-10-30 | Perlu konfirmasi ruang lingkup
TASK-271 | Customer Experience Program | Customer Success | Menyusun rencana tindak lanjut akun | Maya Anggraini | Medium | Blocked | 25 | 2026-09-24 | 2026-12-04 | 35 | No | 2026-10-23 | Menunggu data dari tim terkait
TASK-272 | Procurement Efficiency | Finance & Procurement | Melakukan rekonsiliasi biaya | Aldi Wijaya | Medium | Completed | 100 | 2026-09-26 | 2026-12-04 | 35 | No | 2026-10-25 | Dokumentasi telah diperbarui
TASK-273 | Service Delivery Improvement | Operations | Menindaklanjuti temuan audit | Aldi Wijaya | High | In Progress | 17 | 2026-08-18 | 2026-10-23 | -7 | Yes | 2026-10-26 | Sedang dikerjakan
TASK-274 | Platform Reliability | Product & Engineering | Menulis unit test | Dewi Lestari | Low | In Review | 96 | 2026-09-07 | 2026-12-12 | 43 | No | 2026-10-24 | Menunggu review stakeholder
TASK-275 | Annual Planning | Project Management | Memperbarui risk register | Intan Permata | High | Completed | 100 | 2026-08-17 | 2026-11-11 | 12 | No | 2026-10-24 | Dokumentasi telah diperbarui
TASK-276 | Client Onboarding | Customer Success | Memperbarui knowledge base | Yoga Firmansyah | Medium | In Progress | 21 | 2026-09-04 | 2026-12-09 | 40 | No | 2026-10-26 | Koordinasi lintas tim berlangsung
TASK-277 | Learning & Development | Human Resources | Memantau target rekrutmen | Budi Santoso | Medium | Not Started | 0 | 2026-09-11 | 2026-11-08 | 9 | No | 2026-10-23 | Perlu konfirmasi ruang lingkup
TASK-278 | Performance Management | Human Resources | Menjadwalkan wawancara kandidat | Dimas Saputra | Medium | Completed | 100 | 2026-09-20 | 2026-10-25 | -5 | No | 2026-10-25 | Deliverable sudah diserahkan
TASK-279 | Internal Workflow Automation | Product & Engineering | Melakukan deployment ke production | Kevin Hartono | Critical | Blocked | 50 | 2026-09-13 | 2026-10-20 | -10 | Yes | 2026-10-29 | Menunggu data dari tim terkait
TASK-280 | Internal Workflow Automation | Product & Engineering | Memperbarui dokumentasi teknis | Maya Anggraini | Medium | In Progress | 26 | 2026-08-01 | 2026-11-21 | 22 | No | 2026-10-26 | Sesuai rencana kerja
TASK-281 | Data Quality Initiative | Data & Analytics | Memperbarui pipeline data | Yoga Firmansyah | Medium | In Review | 81 | 2026-08-11 | 2026-10-23 | -7 | Yes | 2026-10-26 | Draft siap ditinjau
TASK-282 | Corporate Communications | Marketing & Communications | Menyiapkan materi media sosial | Budi Santoso | High | Not Started | 0 | 2026-08-12 | 2026-11-06 | 7 | No | 2026-10-27 | Menunggu prioritas sprint
TASK-283 | Customer Experience Program | Customer Success | Menindaklanjuti permintaan pelanggan | Rizky Maulana | Low | Not Started | 0 | 2026-09-13 | 2026-12-02 | 33 | No | 2026-10-29 | Belum dimulai; masuk backlog
TASK-284 | Brand Awareness Campaign | Marketing & Communications | Menyiapkan materi media sosial | Yoga Firmansyah | Low | In Progress | 27 | 2026-08-14 | 2026-10-20 | -10 | Yes | 2026-10-28 | Sesuai rencana kerja
TASK-285 | Sales Performance Analytics | Data & Analytics | Melakukan rekonsiliasi data | Rizky Maulana | Medium | In Review | 86 | 2026-08-02 | 2026-10-23 | -7 | Yes | 2026-10-23 | Perlu validasi akhir
TASK-286 | Brand Awareness Campaign | Marketing & Communications | Menulis draft artikel | Rina Kurnia | Medium | Not Started | 0 | 2026-08-18 | 2026-12-09 | 40 | No | 2026-10-25 | Belum dimulai; masuk backlog
TASK-287 | Internal Workflow Automation | Product & Engineering | Melakukan code review | Andi Pratama | Medium | In Progress | 46 | 2026-08-11 | 2026-12-07 | 38 | No | 2026-10-26 | Koordinasi lintas tim berlangsung
TASK-288 | Corporate Communications | Marketing & Communications | Meninjau brand guideline | Intan Permata | High | Blocked | 13 | 2026-10-05 | 2026-11-05 | 6 | No | 2026-10-24 | Dependensi vendor belum selesai
TASK-289 | Data Quality Initiative | Data & Analytics | Menyusun definisi KPI | Rizky Maulana | Critical | Completed | 100 | 2026-08-10 | 2026-11-21 | 22 | No | 2026-10-24 | Deliverable sudah diserahkan
TASK-290 | Performance Management | Human Resources | Menyiapkan evaluasi kinerja | Andi Pratama | Low | In Progress | 19 | 2026-08-23 | 2026-12-02 | 33 | No | 2026-10-29 | Koordinasi lintas tim berlangsung
TASK-291 | PMO Transformation | Project Management | Memperbarui risk register | Tania Wibowo | Medium | Completed | 89 | 2026-08-06 | 2026-12-07 | 38 | No | 2026-10-24 | Dokumentasi telah diperbarui
TASK-292 | Sales Performance Analytics | Data & Analytics | Melakukan rekonsiliasi data | Fajar Nugroho | Critical | Not Started | 0 | 2026-08-20 | 2026-11-05 | 6 | No | 2026-10-25 | Menunggu prioritas sprint
TASK-293 | Service Delivery Improvement | Operations | Menyusun laporan operasional | Siti Rahma | Medium | In Review | 87 | 2026-08-09 | 2026-11-14 | 15 | No | 2026-10-29 | Menunggu review stakeholder
TASK-294 | SOP Standardization | Operations | Memeriksa checklist operasional | Dewi Lestari | Medium | In Review | 85 | 2026-08-08 | 2026-12-05 | 36 | No | 2026-10-28 | Menunggu review stakeholder
TASK-295 | Enterprise Process Improvement | Project Management | Menyusun weekly status report | Nadia Putri | Medium | In Progress | 43 | 2026-09-14 | 2026-12-10 | 41 | No | 2026-10-28 | Sedang dikerjakan
TASK-296 | Procurement Efficiency | Finance & Procurement | Memperbarui tracking anggaran | Aldi Wijaya | Medium | In Progress | 43 | 2026-09-12 | 2026-11-12 | 13 | No | 2026-10-29 | Koordinasi lintas tim berlangsung
TASK-297 | Client Onboarding | Customer Success | Memvalidasi penyelesaian keluhan | Nadia Putri | Medium | In Progress | 57 | 2026-09-16 | 2026-11-14 | 15 | No | 2026-10-29 | Sedang dikerjakan
TASK-298 | Sales Performance Analytics | Data & Analytics | Menyusun definisi KPI | Intan Permata | Low | Not Started | 0 | 2026-10-05 | 2026-12-05 | 36 | No | 2026-10-23 | Menunggu prioritas sprint
TASK-299 | Talent Acquisition Sprint | Human Resources | Memeriksa kelengkapan dokumen HR | Tania Wibowo | Medium | Not Started | 0 | 2026-08-23 | 2026-12-07 | 38 | No | 2026-10-25 | Menunggu prioritas sprint
TASK-300 | Corporate Communications | Marketing & Communications | Menyiapkan materi media sosial | Nadia Putri | Medium | Completed | 100 | 2026-09-10 | 2026-12-10 | 41 | No | 2026-10-30 | Selesai sesuai rencana